## Readiness
RESEARCHVOICE AI ¦ DEPI FINAL READINESS
Evidence-aware tracking • 27 October 2026 • not yet instructor-approved
ID | Guideline deliverable | Evidence status | Assigned person | Evidence / file | Remaining action
B01 | 1-page Business Brief | Draft ready |  | 01_Business_Discovery/01_Business_Brief.docx | Verify problem-cost number, buyer and KPI assumptions
B02 | 3–5 KPI baseline / target / actual | Needs team evidence |  | 01_Business_Discovery/03_KPI_Table_A4.xlsx | Measure baseline and synthetic test actuals
D01 | Features, integration, safety & evaluation plans | Draft ready |  | 02_Solution_Design/02_Solution_Design.docx | Confirm scope, five component ownership and risk owners
D02 | Instructor single-workflow exception | Awaiting approval |  | 06_Approvals_and_Signoff/Instructor_Review_Request.docx | Attach written instructor approval if available
O01 | Assign five component owners and three shared roles | Needs team evidence |  | 00_START_HERE/Master_Readiness_and_Signoff.xlsx / Owners | Fill five names and roles
W01 | Integrated Phase 4 n8n system | Verified demo |  | 03_Build/ResearchVoice_Phase4_Monitoring_Alerts_IMPORT.json | Verify import credentials/production export date at hand-in
W02 | Five one-page owner documents | Draft ready |  | 03_Build/Owner_Documents/ | Each owner replaces screenshots and signs
T01 | 3 normal + 1 edge + 1 unsafe per component | Needs team evidence |  | 03_Build/Individual_Test_Evidence_Tracker.xlsx | Complete 25 expected/actual records and links
T02 | Three full-system scenarios | Needs team evidence |  | 04_Evaluation/01_Three_End_to_End_Scenarios.docx | One observed complicated case; document typical and refusal
E01 | Independent judge five-dimension rubric | Verified demo |  | 04_Evaluation/03_Evaluation_Test_Report_DRAFT.docx | Preserve frozen pre-human-correction outputs
E02 | Two independent human reviewer scores | Needs team evidence |  | 04_Evaluation/02_Human_Judge_Calibration.xlsx | Two non-builders score same scenarios
E03 | LangSmith QA checkpoint | Verified demo |  | 04_Evaluation/Evidence_Screenshots/EV07_LangSmith_Run.png | Link exact runs to scenario IDs
E04 | Per-step LangSmith trace of each scenario | Needs team evidence |  | 04_Evaluation/03_Evaluation_Test_Report_DRAFT.docx | Existing trace covers QA only; document scope/close gap
M01 | Monitoring metrics and one-page dashboard | Draft ready |  | 04_Evaluation/04_One_Page_Monitoring_Dashboard_DRAFT.pdf | Refresh with measured KPI actuals
M02 | Soft alert and evidence | Verified demo |  | 04_Evaluation/Evidence_Screenshots/EV03_Soft_Alert.png | Link to original execution
M03 | Hard pause alert working | Needs team evidence |  | 04_Evaluation/03_Evaluation_Test_Report_DRAFT.docx | Record guideline-required proof of hard hold
L01 | A5 issue log with status / fix | Draft ready |  | 04_Evaluation/02_Human_Judge_Calibration.xlsx | Validate statuses and assigned owners
L02 | Test Report and limitations | Draft ready |  | 04_Evaluation/03_Evaluation_Test_Report_DRAFT.docx | Insert formal test outcomes, score comparisons, actual KPIs
P01 | Five-presenter slides and script | Draft ready |  | 05_Pitch/ResearchVoice_AI_Final_Business_Pitch_DRAFT.pptx | Replace names, verify facts, rehearse
P02 | Backup recording of full synthetic run | Needs team evidence |  | 05_Pitch/03_Live_Demo_and_Backup_Runbook.docx | Team must actually record and upload video
A01 | Five phase checkpoint approvals | Awaiting approval |  | 06_Approvals_and_Signoff/Team_and_Instructor_Signoff.docx | Instructor reviews and signs checkpoint decisions
A02 | Final shared folder with submitted versions | Draft ready |  | 00_START_HERE/README_FINAL_SUBMISSION.md | Collect signed / measured versions before submission

## Owners
OWNER AND ROLE SIGN-OFF ¦ INSTRUCTOR-APPROVED SINGLE-WORKFLOW EXCEPTION
Component | Function | Member name | Own 5 tests documented? | Own one-pager approved? | Presenter slides | Signature / date
C1 | Study and variable schema | [ASSIGN] | Pending | Pending | Slides 1–3
C2 | Text/voice intake and privacy | [ASSIGN] | Pending | Pending | Slides 4–5
C3 | Schema-constrained extraction | [ASSIGN] | Pending | Pending | Slide 6 + demo
C4 | Independent QA, LangSmith, monitoring | [ASSIGN] | Pending | Pending | Slides 7–8
C5 | Human approval and XLSX export | [ASSIGN] | Pending | Pending | Slides 9–12
Shared role | Assigned member | Accepted on/date
Team Lead
Integration Owner
Evaluation Owner
Instructor exception proof: attach email/message or obtain explicit checkpoint confirmation.

## Checkpoints
DEPI INSTRUCTOR CHECKPOINT REGISTER
Phase | Deliverable | Team ready? | Instructor decision | Date | Instructor feedback / required revisions
1 — Business | One-page Business Brief | Draft only | Pending
2 — Design | Feature list, five cards, map, safety & evaluation plans | Draft only | Pending
3 — Build | Five owner one-pagers, n8n export, case records | Draft only | Pending
4 — Evaluate | Scenarios, tests, LangSmith, dashboard, calibration, KPIs, video | Partial | Pending
5 — Pitch | Slides, live demo, all five members speaking | Draft only | Pending

## Evidence register
EXISTING OBSERVED EVIDENCE ¦ SYNTHETIC CASES ONLY
Exhibit | Claim evidenced | Scope | Source file | Evidence strength | Remaining need
EV01 | Study/schema creation and approval | Oct 26 joint demo | 04_Evaluation/Evidence_Screenshots/EV01_Study_Schema.png | Observed screenshot | Owner run reference
EV02 | Voice → transcription confirmation | Oct 26 joint demo | 04_Evaluation/Evidence_Screenshots/EV02_Voice_Transcript.png | Observed screenshot | Link execution ID
EV03 | Mismatch produced soft alert | Oct 26 joint demo | 04_Evaluation/Evidence_Screenshots/EV03_Soft_Alert.png | Observed screenshot | Link soft-alert execution
EV04 | Manual correction and XLSX delivery | Oct 26 joint demo | 04_Evaluation/Evidence_Screenshots/EV04_Corrected_Export.png | Observed screenshot | Keep actual approved test XLSX
EV05 | /eval 4.6/5 and /monitor rolling counters | Single synthetic case | 04_Evaluation/Evidence_Screenshots/EV05_Eval_Monitor.png | Observed screenshot | Not a clinical accuracy benchmark
EV06 | Successful published n8n execution | Oct 26 joint demo | 04_Evaluation/Evidence_Screenshots/EV06_Execution_Canvas.png | Observed screenshot | Owner sign-off
EV07 | LangSmith QA trace shown in UI | QA checkpoint only | 04_Evaluation/Evidence_Screenshots/EV07_LangSmith_Run.png | Observed screenshot | Per-stage traces missing
OUT01 | Monitoring JSON: soft / unresolved_extraction_issues / 10490ms | Reported output | 04_Evaluation/Observed_Run_Excerpt.md | User-provided JSON | Original execution link
OUT02 | LangSmith ingestion: Run created | Reported output | 04_Evaluation/Observed_Run_Excerpt.md | User-provided JSON | Original LangSmith run link

## Summary
SUBMISSION DECISION ¦ DRAFT ONLY
Final sign-off is NOT complete. Rows are prefilled with only documented status.
Total items | 22
Verified demos | 4
Draft ready | 8
Needs team evidence | 8
Awaiting approval | 2
REQUIRED BEFORE THE TEAM CAN CALL THIS FINAL
1 Enter five owner names, three shared roles and owner signatures.
2 Complete the 25 case records and three end-to-end scenario outcomes.
3 Two independent human reviewers must score frozen model outputs.
4 Measure KPI actuals; do not use planning assumptions as results.
5 Confirm required LangSmith trace coverage and hard-hold behavior.
6 Record the actual backup demo video; add its filename.
7 Obtain instructor checkpoint approvals and verify slide claims.
8 Replace DRAFT files with signed, measured final versions.